## Cronograma
Create professional Gantt charts in GanttPRO in a few clicks
Cronograma | [10 empty] | 2024-02-27 12:18
Color | WBS Number | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Predecessor | Budget | Actual cost | Created | Creator | Type | Project | Level
| 1 | Levantamento Bibliográfico: Artigos, Livros e outros Materiais | Jheickson | 2024-02-09 09:00 | 2024-02-15 18:00 |  | 10 | 40 | 6 | 0 | In progress | Highest |  | 0 | 0 | 2024-02-20 15:08 | Felipe Santos | task | Cronograma | 1
| 2 | Levantamento Bibliográfico: Mapear outras ferramentas similares | Jheickson | 2024-02-09 09:00 | 2024-02-15 18:00 |  | 25 | 40 | 3 | 0 | In progress | Highest |  | 0 | 0 | 2024-02-27 08:51 | Felipe Santos | task | Cronograma | 1
| 3 | Levantamento Bibliográfico: Analisar estudos sobre a efetividade de layouts | Jheickson | 2024-02-09 09:00 | 2024-02-15 18:00 |  | 30 | 40 | 8 | 0 | In progress | Highest |  | 0 | 0 | 2024-02-27 08:52 | Felipe Santos | task | Cronograma | 1
| 4 | Levantamento de Requisitos: Definir os objetivos claramente | Jheickson | 2024-02-09 09:00 | 2024-02-15 18:00 |  | 0 | 40 | 6 | 0 | Open | Highest |  | 0 | 0 | 2024-02-27 08:52 | Felipe Santos | task | Cronograma | 1
| 5 | Levantamento de Requisitos: Identificar necessidades dos possíveis usuários | Jheickson | 2024-02-09 09:00 | 2024-02-15 18:00 |  | 15 | 40 | 6 | 0 | In progress | Highest |  | 0 | 0 | 2024-02-27 08:53 | Felipe Santos | task | Cronograma | 1
| 6 | Levantamento de Requisitos: Analisar funcionalidades de ferramentas existentes | Jheickson | 2024-02-09 09:00 | 2024-02-15 18:00 |  | 40 | 40 | 4 | 0 | In progress | Highest |  | 0 | 0 | 2024-02-27 08:53 | Felipe Santos | task | Cronograma | 1
| 7 | Levantamento de Requisitos: Identificar oportunidades de aprimoramento | Jheickson | 2024-02-09 09:00 | 2024-02-15 18:00 |  | 0 | 40 | 2 | 0 | Open | Highest |  | 0 | 0 | 2024-02-27 08:53 | Felipe Santos | task | Cronograma | 1
| 8 | Análise de Viabilidade: Avaliar viabilidade técnica, economica e temporal | Jheickson | 2024-02-20 09:00 | 2024-02-26 18:00 |  | 50 | 40 | 10 | 0 | In progress | Medium |  | 0 | 0 | 2024-02-27 08:53 | Felipe Santos | task | Cronograma | 1
| 9 | Análise de Viabilidade: Definir tecnologias para desenvolvimento | Jheickson | 2024-02-20 09:00 | 2024-02-26 18:00 |  | 50 | 40 | 8 | 0 | In progress | Medium |  | 0 | 0 | 2024-02-27 08:53 | Felipe Santos | task | Cronograma | 1
| 10 | Análise de Viabilidade: Estimar tempo e recursos necessários | Jheickson | 2024-02-20 09:00 | 2024-02-26 18:00 |  | 30 | 40 | 6 | 0 | In progress | Medium |  | 0 | 0 | 2024-02-27 08:54 | Felipe Santos | task | Cronograma | 1
| 11 | Especificação Funcional: Descrever as funcionalidades do WebApp | Jheickson | 2024-03-01 09:00 | 2024-03-07 18:00 |  | 0 | 40 | 8 | 0 | Open | Highest |  | 0 | 0 | 2024-02-27 08:54 | Felipe Santos | task | Cronograma | 1
| 12 | Especificação Funcional: Prototipagem da interface | Jheickson | 2024-03-01 09:00 | 2024-03-07 18:00 |  | 0 | 40 | 12 | 0 | Open | Highest |  | 0 | 0 | 2024-02-27 08:54 | Felipe Santos | task | Cronograma | 1
| 13 | Especificação Funcional: Definir estrutura de dados e APIs | Jheickson | 2024-03-01 09:00 | 2024-03-07 18:00 |  | 0 | 40 | 16 | 0 | Open | Highest |  | 0 | 0 | 2024-02-27 08:55 | Felipe Santos | task | Cronograma | 1
| 14 | Especificação Técnica: Definir arquitetura (Frameworks, libraries, etc) | Jheickson | 2024-03-01 09:00 | 2024-03-07 18:00 |  | 0 | 40 | 8 | 0 | Open | Highest |  | 0 | 0 | 2024-02-27 08:55 | Felipe Santos | task | Cronograma | 1
| 15 | Especificação Técnica: Estabelecer padrão de Desenvolvimento | Jheickson | 2024-03-01 09:00 | 2024-03-07 18:00 |  | 0 | 40 | 6 | 0 | Open | Highest |  | 0 | 0 | 2024-02-27 08:56 | Felipe Santos | task | Cronograma | 1
| 16 | Elaboração do Projeto: Iniciar o processo de escrita do artigo | Jheickson | 2024-05-01 09:00 | 2024-05-07 18:00 |  | 0 | 40 | 6 | 0 | Open | Medium |  | 0 | 0 | 2024-02-27 08:56 | Felipe Santos | task | Cronograma | 1
| 17 | Desenvolvimento do WebApp: Implementar funcionalidades fundamentais | Jheickson | 2024-03-15 09:00 | 2024-03-21 18:00 |  | 0 | 40 | 20 | 0 | Open | Medium |  | 0 | 0 | 2024-02-27 08:56 | Felipe Santos | task | Cronograma | 1
| 18 | Desenvolvimento do WebApp: Implementar interface | Jheickson | 2024-03-15 09:00 | 2024-03-21 18:00 |  | 0 | 40 | 20 | 0 | Open | Medium |  | 0 | 0 | 2024-02-27 08:56 | Felipe Santos | task | Cronograma | 1
| 19 | Desenvolvimento do WebApp: Testes/Bugs | Jheickson | 2024-03-15 09:00 | 2024-03-21 18:00 |  | 0 | 40 | 10 | 0 | Open | Medium |  | 0 | 0 | 2024-02-27 08:57 | Felipe Santos | task | Cronograma | 1
| 20 | Documentação: Manual do Usuário | Jheickson | 2024-04-01 09:00 | 2024-04-05 18:00 |  | 0 | 40 | 6 | 0 | Open | Low |  | 0 | 0 | 2024-02-27 08:57 | Felipe Santos | task | Cronograma | 1
| 21 | Documentação: Guia de instalação | Jheickson | 2024-04-01 09:00 | 2024-04-05 18:00 |  | 0 | 40 | 4 | 0 | Open | Low |  | 0 | 0 | 2024-02-27 08:57 | Felipe Santos | task | Cronograma | 1
| 22 | Documentação: Documentação técnica | Jheickson | 2024-04-01 09:00 | 2024-04-05 18:00 |  | 0 | 40 | 12 | 0 | Open | Medium |  | 0 | 0 | 2024-02-27 08:57 | Felipe Santos | task | Cronograma | 1
| 23 | Testes de Usabilidade: Testes com usuários reais | Jheickson | 2024-04-15 09:00 | 2024-04-19 18:00 |  | 0 | 40 | 14 | 0 | Open | Medium |  | 0 | 0 | 2024-02-27 08:57 | Felipe Santos | task | Cronograma | 1
| 24 | Testes de Usabilidade: Analisar feedback | Jheickson | 2024-04-15 09:00 | 2024-04-19 18:00 |  | 0 | 40 | 8 | 0 | Open | Medium |  | 0 | 0 | 2024-02-27 08:58 | Felipe Santos | task | Cronograma | 1
This document has been created with the help of https://ganttpro.com online service